## Sprint 1 Example
Webravo Excalibur Burn Chart
Sprint | # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
| Points Target | 0 | Story Points in sprint after Sprint Planning | [8 empty] | Days elapsed
| Number of Stories | 22 | Stories in sprint after Sprint Planning
0
[13 empty] | of | 4
Points | Day | 1 | 2 | 3 | 4 | 5
| Forecast Burn | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | Points
| Required Burn | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A
| Mangler | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | Out of
| Done today | 0 | [10 empty] | 0
| Done | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Stories | Elapsed Days | [10 empty] | Stories done
Done
fill or leave blank as required >> | Test | [10 empty] | #N/A | Out of
fill or leave blank as required >> | 50% | [11 empty] | 22
fill or leave blank as required >> | Hvis der er tid
fill or leave blank as required >> | [11 empty] | Takt
fill or leave blank as required >>
fill or leave blank as required >> | [11 empty] | #N/A
To Do
Change From Planned

## Instructions
Sprint Burn Down Templates
Instructions: What are these charts? How do I work them?
Updated 2020
Classic Agile Iteration Charts
• A Burn DOWN for hours (and a version without this, as it's a bit out of fashion these days) • A Burn UP for story points • A Cumulative flow chart to help you to identify bottlenecks in your workflow.
How do I use this Template?
• Choose "Make a copy" from the "File" menu above. • This will save an editable version to your own Google Drive. • Overwrite the content of the white cells, don't delete rows or the calcs in the grey or coloured cells! • By entering data in the input grids, the charts will just happen • Even if you don't use all of the Cumulative flow, keep track of stories completed in the "Done" row
What do the charts show?
Burn Down
Estimated number of hours remaining to complete the sprint goal.
• Normally updated each day, immediately after the stand-up meeting • The Scrum Master adds up all of the estimated hours remaining on all incomplete user stories • Also shows the total number of hours available to the team in the remaining days of the sprint • So, it's designed whether things are on track, ahead or behind schedule • In recent experience (2020), fewer teams do this. So there's a version here without this chart included
Burn Up
Story points completed daily, throughout a sprint.
• Very similar to the burn down • Rather than tracking work still to be done, it tracks work that has been completed • Shows the accumulation of "Done" story points throughout the course of a sprint.
Cumulative Flow
Tracks: Efficiency through stages in the delivery process
• Highlights workflow bottlenecks, by charting the progress of stories through each stage of the sprint • The coloured bands each represent one stage in the development workflow • In a “pull” system, a widening of a coloured bands will indicate a bottleneck in the phase that follows • It could in practice though (when used in Scrum), indicate a lag in the phase itself
Let me know how you go!
You are free copy this doc, and use it in any way you like. Knock yourself out. It'd be great if you could post a link back to the blog (somewhere) if you find the charts give you some help at work!
http://scrumage.com/
If you find any errors, or think of ways to improve these charts, don't keep it to yourself. Any feedback at all is great.
Adrian
adrian@fittolani.com

## Sprint 1 Example (with Hrs Burn
Sprint | # Team Members | 8 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 7.5 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 10 | Total number of work days in Sprint (exclude public holidays etc)
| Points Target | 36 | Story Points in sprint after Sprint Planning
| Number of Stories | 8 | Stories in sprint after Sprint Planning
Hours | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Available | 600 | 540 | 480 | 420 | 360 | 300 | 240 | 180 | 120 | 60 | Days | 7
| Task Hrs Remaining | 400 | 400 | 380 | 400 | 300 | 300 | 300 |  |  |  | Points | 20
[12 empty] | Stories | 5
Points | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Takt | 1.4
| Forecast Burn | 2.8571 | 5.7143 | 8.5714 | 11.4286 | 14.2857 | 17.1429 | 20 | 22.8571 | 25.7143 | 28.5714
| Required Burn | 3.6 | 7.2 | 10.8 | 14.4 | 18 | 21.6 | 25.2 | 28.8 | 32.4 | 36
| Done | 3 | 6 | 11 | 11 | 19 | 19 | 20
Stories | Elapsed Days | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Done | 1 | 2 | 3 | 3 | 4 | 4 | 5
fill or leave blank as required >>
fill or leave blank as required >>
fill or leave blank as required >>
fill or leave blank as required >>
fill or leave blank as required >> | Process B (eg ("Test") | 0 | 1 | 2 | 1 | 1 | 2 | 1
fill or leave blank as required >> | Process A (eg "Dev") | 3 | 2 | 2 | 3 | 3 | 2 | 2
| To Do | 4 | 3 | 1 | 1 | 0 | 0 | 0
| Change From Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0